Online course development process (for faculty)

Exploration Stage

- FAC discussions on strategic goals of overall online course development

- FAC/Admin competitive analysis

- FAC discussion/decision on courses to develop (and priority)

- FAC discussion/decision on modes of delivery, online teaching pedagogical goals

- FAC/Admin discussion/decision on policies and procedures

Planning Stage

- Discuss course online activity and assessment strategy with developer

- Plan individual course delivery strategy and applications to be used

- Establish course plan and timeline with developer

- Decide on instructors for sections of course (if multiple sections of course are offered)

- Decide on course graphic look

- Plan marketing strategy

Content Creation Stage

- Complete syllabus

- Complete (weekly) lesson plans

- Request a developmental course be created in WebCT Vista

(request previous course be used as a template or use general template or start with blank course)

- Create PowerPoint graphics (developer)

- Create PowerPoint

- Create script in PowerPoint slide notes

- Use audio recorder to record lecture (attached instructions for Olympus WS100)

- Upload files to appropriate folders on Vista or network drive

- Email developer that files are uploaded

- Compile lectures (developer)(example lecture)

- Create introductory video(s) of developer and instructors (example video)

Implementation Stage

- Get copyright clearance for course materials, create e-reserves, order books from bookstore

- Walk-through course design with developer (approve moving course from development mode to live mode)

- Recruit and Register students (admin)

- Meet with developer to familiarize yourself with teaching with Vista

- Meet/correspond with any adjunct faculty teaching sections of course

- Instructor email students welcome, instructions for using Vista and required book list (one week befor start of class).

- Create student groups as necessary in Vista